## Sheet1
Project Phase | Document | Purpose | Content | Prepared by | Approved by | Notes
Initiating | Project Request or Statement of Work | A narrative description of products, services, or results to be delivered by the project | Business Need, Product scope description, Alignment with Strategic plan | Customer or Project Initiator | Governance
| Business Case | To determine if project is worth the investment | Cost Benefit analysis including total cost of ownership | Business or Financial Analyst | Governance
| Project Charter | Formally authorizes the project | Project Purpose, Project objectives and success criteria, High level requirements, High level risks, Summary milestone schedule, Summary budget, Stakeholder list, Project approval requirements, Roles and responsibilities | Sponsor and Project Manager | Sponsor(s)
Planning | Project Plan (combination of sub plans) |  |  | Project Manager and project team | Sponsor(s), applicable resource managers | With the exception of the baselines, all project documents are living documents which are updated as the project executes.
| Scope baseline | Baseline for tracking scope | Defines the scope in detail | Project Manager and project team | Sponsor(s), applicable resource managers
| Detailed Requirements | Baseline for tracking requirements | Defines requirements and completion criteria in detail tied to deliverable | Project Manager and project team | Sponsor(s), applicable resource managers
| Schedule Baseline | Baseline for tracking schedule | WBS structure, detailed activity list with dependencies, milestones | Project Manager and project team | Sponsor(s), applicable resource managers | This is not a form but is completed in a tracking tool - e.g. Basecamp or MS Project
| Cost Baseline | Baseline for tracking cost | Detailed cost breakdown for personnel, non-personnel operational and capital expenses, including contingency reserves | Project Manager and project team | Sponsor(s), applicable resource managers
| Risk Management | Identification and strategies for managing risks | Outlines risks, prioritizes them, and provides mitigation strategies | Project Manager and project team | Sponsor(s), applicable resource managers
| Stakeholder Management | Outlines stakeholder management | Identification, assessment, and classification of project stakeholders | Project Manager and project team | This is an internal document for the project manager | This is an internal document for the project manager
| Communications | Outlines communication strategy, tools and techniques to be used. | Describes how, when and by whom information about the project will be administered and disseminated | Project Manager and project team | Sponsor(s), applicable resource managers
| Project Governance | Outlines how the project will be governed | Outlines project success metrics, change management procedures, meeting and sponsor reporting cadence, thresholds for action | Project Manager | Sponsor(s), applicable resource managers | This will likely be standard for all projects unless there are exceptions
| Procurement | Identifies all contracts and who manages them. | List of contracts, who manages them, close-out criteria | Project Manager | Sponsor(s), applicable resource managers
| Project Kick-Off | Standard Project kick-off agenda | Outlines Project Kick-off agenda | Project Manager | N/A
Executing | Change Request | Request form to modify or add a requirement or deliverable | Outlines impact and schedule for requested change | Sponsor, client, or team member | Project Change Control Board
| Change Control Log | History of requests and their status | Records each request and if approved/implemented or put on hold | Project Manager | N/A
| Issue Log | Documents project issues | Issue and person assigned person to resolve | Project Manager | N/A
Monitoring and Controlling | Project Status Meeting Template | Outlines format for project status meeting | Notes and action items for each meeting | Project Manager | N/A
| Individual Project Status Report | Provides scheduled updates to Sponsors | Status on budget, schedule, scope, risks and key milestones | Project Manager | N/A | Weekly or bi-weekly depending on sponsor
| Consolidated Dashboard | Provides high level project status | Consolidated status for budget, schedule, and scope | Project Manager | N/A | Bi-weekly report
Close-Out | Project sign-off | Authorizes the project to be released | Deliverable status, outstanding issues, final QA report | Project Manager | Sponsor(s)
| Lessons Learned | Provides a history of project success/failures as a reference for future projects. | Documents projects failures, successes | Project Manager and Team | N/A
| Transition to Operations Checklist and documentation | Provides project/product information so operations can successfully maintain | Development support contacts, outstanding issues and work-arounds, product documentation and training manuals | Project Manager and Team | Operations